## Sheet3
THE SILK RESIDENCES PROJECT
Ramon Magsaysay Corner, Santol St., Sta. Mesa, Manila
2017-06-10
DAILY MANPOWER REPORT
INDIRECT LABOR | [7 empty] | DIRECT LABOR |  | R | P | A | OL | AS | NR
A. SITE MANAGEMENT/ SUPERVISION |  | R | P | A | OL | AS | NR | 1 | FOREMAN(STAFF) | 1 | 1 | 0 | 0 | 0 | 0
1 | PROJECT MANAGER | 1 | 1 | 0 | 0 | 0 | 0 | 2 | FOREMAN (ARCHITECTURAL)(STAFF) | 1 | 1 | 0 | 0 | 0 | 0
2 | ARCHITECTURAL PROJECT SUPERINTENDENT | 1 | 1 | 0 | 0 | 0 | 0 | 3 | FOREMAN (PAINTER)(STAFF) | 1 | 1 | 0 | 0 | 0 | 0
3 | FIELD ENGINEER | 2 | 2 | 0 | 0 | 0 | 0 | 4 | FOREMAN(MEPFS)(STAFF) | 1 | 0 | 0 | 0 | 0 | 1
4 | PROJECT SUPERITENDENT | 1 | 1 | 0 | 0 | 0 | 0 | 5 | DATAWALL INSTALLER | 16 | 14 | 1 | 0 | 0 | 1
5 | FORMWORKS ENGINEER | 1 | 1 | 0 | 0 | 0 | 0 | 6 | ELECTRICIAN | 5 | 4 | 1 | 0 | 0 | 0
6 | PRECAST ENGINEER | 1 | 1 | 0 | 0 | 0 | 0 | 7 | ELECTRICIAN, JR | 54 | 36 | 3 | 0 | 0 | 15
7 | MEPFS HEAD | 1 | 0 | 1 | 0 | 0 | 0 | 8 | FINISHING CARPENTER | 38 | 30 | 2 | 1 | 0 | 5
8 | PROJECT ARCHITECT | 4 | 3 | 1 | 0 | 0 | 0 | 9 | FINISHING MASON | 87 | 67 | 7 | 3 | 1 | 9
9 | PROJECT ENGINEER (MEPFS) | 2 | 2 | 0 | 0 | 0 | 0 | 10 | FOREMAN (MASON) | 1 | 1 | 0 | 0 | 0 | 0
10 | QA/QC ARCHITECT SR. | 1 | 1 | 0 | 0 | 0 | 0 | 11 | FOREMAN (MEPFS) | 3 | 3 | 0 | 0 | 0 | 0
11 | QA/QC ENGINEER SR. | 1 | 1 | 0 | 0 | 0 | 0 | 12 | FOREMAN (PRECAST) | 1 | 1 | 0 | 0 | 0 | 0
12 | QUANTITY SURVEYOR | 2 | 1 | 1 | 0 | 0 | 0 | 13 | FOREMAN (SCAFFOLDER) | 1 | 1 | 0 | 0 | 0 | 0
13 | QUANTITY SURVEYOR HEAD | 1 | 1 | 0 | 0 | 0 | 0 | 14 | FORMWORKS CARPENTER | 23 | 20 | 2 | 1 | 0 | 0
| SubTotal | 19 | 16 | 3 | 0 | 0 | 0 | 15 | HELPER | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 16 | HELPER ELECTRICIAN | 3 | 1 | 0 | 0 | 0 | 2
B. LINE & GRADE / SURVEY TEAM |  | R | P | A | OL | AS | NR | 17 | HELPER PLUMBER | 2 | 1 | 1 | 0 | 0 | 0
1 | SURVEYOR | 1 | 1 | 0 | 0 | 0 | 0 | 18 | INSTALLER | 23 | 15 | 3 | 1 | 0 | 4
2 | INSTRUMENTMAN | 2 | 1 | 1 | 0 | 0 | 0 | 19 | LEADMAN CARPENTER | 9 | 8 | 0 | 0 | 0 | 1
3 | SURVEY AIDE | 7 | 6 | 0 | 1 | 0 | 0 | 20 | LEADMAN DATAWALL INSTALLER | 2 | 2 | 0 | 0 | 0 | 0
| SubTotal | 10 | 8 | 1 | 1 | 0 | 0 | 21 | LEADMAN ELECTRICIAN | 4 | 2 | 0 | 0 | 1 | 1
[8 empty] | 22 | LEADMAN INSTALLER | 3 | 3 | 0 | 0 | 0 | 0
C. ADMINISTRATIVE & CLERICAL WORKS |  | R | P | A | OL | AS | NR | 23 | LEADMAN LABORER | 4 | 4 | 0 | 0 | 0 | 0
1 | PROJECT ACCOUNTANT | 1 | 1 | 0 | 0 | 0 | 0 | 24 | LEADMAN MASON | 14 | 12 | 0 | 0 | 0 | 2
2 | CADD OPERATOR | 2 | 2 | 0 | 0 | 0 | 0 | 25 | LEADMAN PAINTER | 5 | 5 | 0 | 0 | 0 | 0
3 | CADD OPERATOR (MEPFS) | 2 | 2 | 0 | 0 | 0 | 0 | 26 | LEADMAN PLUMBER | 5 | 5 | 0 | 0 | 0 | 0
4 | TSD HEAD | 1 | 1 | 0 | 0 | 0 | 0 | 27 | LEADMAN SCAFFOLDER | 4 | 3 | 0 | 0 | 0 | 1
5 | DOCUMENT CONTROL CLERK | 1 | 1 | 0 | 0 | 0 | 0 | 28 | LEADMAN SEALANT APPLICATOR | 1 | 1 | 0 | 0 | 0 | 0
6 | INTERNAL AUDIT STAFF | 1 | 1 | 0 | 0 | 0 | 0 | 29 | LEADMAN STEELMAN | 2 | 2 | 0 | 0 | 0 | 0
7 | PROJECT ADMIN STAFF | 1 | 1 | 0 | 0 | 0 | 0 | 30 | LEADMAN TILESETTER | 3 | 2 | 0 | 0 | 0 | 1
8 | PROJECT NURSE | 1 | 0 | 0 | 1 | 0 | 0 | 31 | LEADMAN WELDER | 1 | 1 | 0 | 0 | 0 | 0
9 | TIMEKEEPER, JR. | 1 | 1 | 0 | 0 | 0 | 0 | 32 | MASON | 1 | 1 | 0 | 0 | 0 | 0
10 | WAREHOUSEMAN | 1 | 1 | 0 | 0 | 0 | 0 | 33 | MASTER PLUMBER | 1 | 1 | 0 | 0 | 0 | 0
11 | WAREHOUSEMAN, JR. | 1 | 1 | 0 | 0 | 0 | 0 | 34 | PAINTER | 55 | 46 | 5 | 4 | 0 | 0
12 | QA/QC AIDE | 1 | 1 | 0 | 0 | 0 | 0 | 35 | PLUMBER | 2 | 0 | 0 | 0 | 0 | 2
13 | TIMEKEEPER AIDE | 2 | 0 | 1 | 1 | 0 | 0 | 36 | PLUMBER, JR | 74 | 47 | 1 | 2 | 1 | 23
14 | UTILITY/MESSENGER | 2 | 0 | 2 | 0 | 0 | 0 | 37 | RIGGER | 3 | 3 | 0 | 0 | 0 | 0
15 | WAREHOUSE AIDE | 2 | 0 | 2 | 0 | 0 | 0 | 38 | ROUGH MASON | 2 | 1 | 1 | 0 | 0 | 0
| SubTotal | 20 | 13 | 5 | 2 | 0 | 0 | 39 | ROUGH PAINTER | 6 | 6 | 0 | 0 | 0 | 0
[8 empty] | 40 | SCAFFOLDER | 27 | 14 | 3 | 0 | 0 | 10
D. SAFETY |  | R | P | A | OL | AS | NR | 41 | SEALANT APPLICATOR | 8 | 7 | 1 | 0 | 0 | 0
1 | SAFETY ENFORCER | 1 | 1 | 0 | 0 | 0 | 0 | 42 | STEELMAN | 16 | 13 | 2 | 0 | 1 | 0
2 | SAFETY OFFICER | 1 | 1 | 0 | 0 | 0 | 0 | 43 | TILESETTER | 18 | 3 | 11 | 0 | 0 | 4
| SubTotal | 2 | 2 | 0 | 0 | 0 | 0 | 44 | TILESETTER MASON | 19 | 11 | 0 | 1 | 0 | 7
[8 empty] | 45 | WELDER | 17 | 11 | 0 | 1 | 0 | 5
E. EQUIPMENT OPERATORS |  | R | P | A | OL | AS | NR | TOTAL DIRECT |  | 567 | 411 | 44 | 14 | 4 | 94
1 | TOWER CRANE OPERATOR(staff) | 1 | 1 | 0 | 0 | 0 | 0
2 | DRIVER, ELF(STAFF) | 1 | 1 | 0 | 0 | 0 | 0 | DISTRIBUTION OF LABORER |  | R | P | A | OL | AS | NR
3 | BOOM TRUCK DRIVER | 0 | 0 | 0 | 0 | 0 | 0 | 1 | BARRACK'S IN-CHARGE | 1 | 1 | 0 | 0 | 0 | 0
4 | SERVICE DRIVER (mangaoang) | 1 | 1 | 0 | 0 | 0 | 0 | 2 | DFOR ENCODER(MEPFS) | 1 | 1 | 0 | 0 | 0 | 0
5 | GENSET OPERATOR | 1 | 1 | 0 | 0 | 0 | 0 | 3 | DOORMAN | 5 | 3 | 1 | 1 | 0 | 0
6 | PUMPCRETE OPERATOR | 1 | 1 | 0 | 0 | 0 | 0 | 4 | FINISHING MASON | 2 | 2 | 0 | 0 | 0 | 0
7 | SERVICE ELEVATOR OPERATOR | 2 | 1 | 0 | 1 | 0 | 0 | 5 | FIRE PRO | 4 | 4 | 0 | 0 | 0 | 0
8 | SKID LOADER OPERATOR | 1 | 1 | 0 | 0 | 0 | 0 | 6 | FORMWORKS WAREHOUSE | 6 | 5 | 1 | 0 | 0 | 0
9 | TOWER CRANE OPERATOR | 1 | 1 | 0 | 0 | 0 | 0 | 7 | HAULER | 5 | 2 | 2 | 0 | 0 | 1
| SubTotal | 9 | 8 | 0 | 1 | 0 | 0 | 8 | HELPER ELECTRICIAN | 9 | 8 | 0 | 0 | 0 | 1
F. MAINTENANCE |  | R | P | A | OL | AS | NR | 9 | HELPER PLUMBER | 9 | 7 | 0 | 0 | 0 | 2
1 | ELECTRICIAN, JR | 1 | 1 | 0 | 0 | 0 | 0 | 10 | HOUSEKEEPING/SAFETY CREW | 3 | 3 | 0 | 0 | 0 | 0
2 | HELPER ELECTRICIAN | 1 | 1 | 0 | 0 | 0 | 0 | 11 | INSTALLER | 1 | 1 | 0 | 0 | 0 | 0
3 | PLUMBER, JR | 1 | 1 | 0 | 0 | 0 | 0 | 12 | LABORER(EQUIPMENT MONITORING) | 1 | 1 | 0 | 0 | 0 | 0
| SubTotal | 3 | 3 | 0 | 0 | 0 | 0 | 13 | PLUMBER/MAINTENANCE | 2 | 2 | 0 | 0 | 0 | 0
[8 empty] | 14 | PRECAST | 6 | 6 | 0 | 0 | 0 | 0
NIGHT SHIFT from PREVIOUS DATE |  | 2016-07-19 | [5 empty] | 15 | PUMPCREW | 9 | 2 | 1 | 1 | 0 | 5
INDIRECT LABOR | [7 empty] | 16 | QC AIDE | 1 | 0 | 0 | 0 | 0 | 1
A. ADMINISTRATIVE & CLERICAL WORKS |  | R | P | A | OL | AS | NR | 17 | SCAFFOLDER | 1 | 1 | 0 | 0 | 0 | 0
1 | FIELD ENGINEER | 1 | 1 | 0 | 0 | 0 | 0 | 18 | SURVEY AIDE | 2 | 1 | 1 | 0 | 0 | 0
[8 empty] | 19 | TIMEKEEPER AIDE | 1 | 1 | 0 | 0 | 0 | 0
B. SAFETY |  | R | P | A | OL | AS | NR | 20 | UTILITY | 1 | 1 | 0 | 0 | 0 | 0
1 | SAFETY ENFORCER | 1 | 1 | 0 | 0 | 0 | 0 | 21 | WAREHOUSE ADMIN | 2 | 2 | 0 | 0 | 0 | 0
[8 empty] | 22 | WAREHOUSE(PRECAST) | 1 | 1 | 0 | 0 | 0 | 0
C. EQUIPMENT OPERATORS |  | R | P | A | OL | AS | NR | 23 | WAREHOUSE(PLUMBER) | 1 | 0 | 0 | 1 | 0 | 0
1 | TOWER CRANE OPERATOR(STAFF) | 1 | 1 | 0 | 0 | 0 | 0 | 24 | WELDER | 3 | 3 | 0 | 0 | 0 | 0
2 | TOWER CRANE OPERATOR | 1 | 1 | 0 | 0 | 0 | 0 | TOTAL |  | 77 | 58 | 6 | 3 | 0 | 10
3 | PUMPCRETE OPERATOR | 1 | 1 | 0 | 0 | 0 | 0 | NIGHT SHIFT
4 | SERVICE ELEVATOR OPERATOR | 1 | 1 | 0 | 0 | 0 | 0 | 1 | BARRACK'S IN-CHARGE | 1 | 1 | 0 | 0 | 0 | 0
5 | SKID LOADER OPERATOR | 1 | 0 | 1 | 0 | 0 | 0 | 2 | PLUMBER/MAINTENANCE | 1 | 1 | 0 | 0 | 0 | 0
6 | LEADMAN MASON(MONITORING) | 1 | 1 | 0 | 0 | 0 | 0 | 3 | ACT. LEADMAN(HAULER) | 1 | 0 | 1 | 0 | 0 | 0
7 | RIGGER (EQUIPMENT MONITORING) | 1 | 1 | 0 | 0 | 0 | 0 | 4 | HAULER | 7 | 5 | 2 | 0 | 0 | 0
8 | DRIVER, MINI DUMPTRUCK (menor) | 1 | 1 | 0 | 0 | 0 | 0 | 5 | PRECAST | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 6 | WAREHOUSE(ELECTRICAL) | 1 | 1 | 0 | 0 | 0 | 0
D. MAINTENANCE |  | R | P | A | OL | AS | NR | 7 | WAREHOUSE(PLUMBER) | 0 | 0 | 0 | 0 | 0 | 0
1 | ELECTRICIAN, JR | 2 | 2 | 0 | 0 | 0 | 0 | 8 | TIMEKEEPER AIDE | 1 | 1 | 0 | 0 | 0 | 0
2 | HELPER ELECTRICIAN | 0 | 0 | 0 | 0 | 0 | 0 | TOTAL |  | 12 | 9 | 3 | 0 | 0 | 0
3 | PLUMBER, JR | 1 | 1 | 0 | 0 | 0 | 0 | SUBCONTRACTOR |  | R | P | A | OL | AS | NR
TOTAL INDIRECT |  | 12 | 11 | 1 | 0 | 0 | 0 | 1 | BUFFER PRECAST | 7 | 7 | 0 | 0 | 0 | 0
[8 empty] | 2 | CITIARE | 6 | N/A | 6 | 0 | 0 | 0
DIRECT LABOR |  | R | P | A | OL | AS | NR | 3 | Grand Nova | 2 | 2 | 0 | 0 | 0 | 0
1 | RIGGER | 2 | 2 | 0 | 0 | 0 | 0 | 4 | I-CONSTECH | 6 | N/A | 6 | 0 | 0 | 0
2 | DATAWALL INSTALLER | 4 | 4 | 0 | 0 | 0 | 0 | 5 | ISDN | 2 | N/A | 2 | 0 | 0 | 0
3 | LEADMAN LABORER | 0 | 0 | 0 | 0 | 0 | 0 | 6 | JEFF JAMES INC. | 18 | 18 | 0 | 0 | 0 | 0
4 | QA/QC AIDE | 1 | 1 | 0 | 0 | 0 | 0 | 7 | INTEGRATED(IBTW) | 8 | 7 | 1 | 0 | 0 | 0
5 | LEADMAN MASON | 1 | 1 | 0 | 0 | 0 | 0 | 8 | NAPAROTA | 74 | 65 | 9 | 0 | 0 | 0
6 | FINISHING MASON | 10 | 8 | 2 | 0 | 0 | 0 | 9 | VCF INSOLATION | 4 | 4 | 0 | 0 | 0 | 0
7 | ROUGH MASON | 0 | 0 | 0 | 0 | 0 | 0 | 10 | YYD SYSTEM-INTERIORS | 2 | N/A | 2 | 0 | 0 | 0
8 | HELPER(WAREHOUSE PLUMBER) | 1 | 1 | 0 | 0 | 0 | 0 |  | TOTAL SUBCON | 129 | 103 | 26 | 0 | 0 | 0
9 | WAREHOUSE AIDE | 1 | 1 | 0 | 0 | 0 | 0
TOTAL DIRECT |  | 20 | 18 | 2 | 0 | 0 | 0 | RESCUE WORKERS |  | R | P | A | OL | AS | NR
[8 empty] | 1 | QA/QC AIDE | 1 | 0 | 1 | 0 | 0 | 0
TOTAL SUMMARY |  | Roster | Present | Absent | On Leave | AS | NR | 2 | PUMPCRETE OPERATOR(N/S) | 0 | 0 | 0 | 0 | 0 | 0
Indirect Labor |  | 63 | 53 | 7 | 3 | 0 | 0 |  | TOTAL RESCUE | 1 | 0 | 1 | 0 | 0 | 0
Indirect Labor(prev. date) |  | 13 | 13 | 0 | 0 | 0 | 0
Direct Labor |  | 644 | 469 | 50 | 17 | 4 | 104
Direct Labor(prev. date) |  | 32 | 30 | 2 | 0 | 0 | 0 | Legend: | R-Roster, P-Present, A-Absent, OL-On Leave, AS-Administrative Suspension, NR-Not Required, D/S-Day Shift, N/S-Night Shift, M/S-Mid Shift, NS-No Submission, OC-On Call, NA-No Activity
Subcontractor |  | 130 | 103 | 27 | 0 | 0 | 0
Rescue Workers |  | 1 | 1 | 0 | 0 | 0 | 0
GRAND TOTAL |  | 883 | 669 | 86 | 20 | 4 | 104
[8 empty] | Prepared by: |  | Noted by:
[8 empty] | SHERYLL ROSE A. BRIOSO |  | JOSEPH BRYAN T. MANALOTO
[8 empty] | Jr. Timekeeper |  | Project Manager
Note on C58: silk7: Farin (Staff)
Note on C59: silk7: sadino
Note on C63: CABRERA & TAROJA
Note on L75: BLANCO
Note on C103: 1=SEGARINO 9=GUERRA GRP
Note on C106: warehouse AIDE MATA

## Sheet1
THE SILK RESIDENCES PROJECT
Ramon Magsaysay Corner, Santol St., Sta. Mesa, Manila
2018-11-22
DAILY MANPOWER REPORT
INDIRECT LABOR | [7 empty] | DIRECT LABOR |  | R | P | A | OL | AS | NR
A. SITE MANAGEMENT/ SUPERVISION |  | R | P | A | OL | AS | NR | 1 | DATAWALL INSTALLER | 5 | 5 | 0 | 0 | 0 | 0
1 | PROJECT MANAGER | 1 | 0 | 0 | 0 | 0 | 1 | 2 | ELECTRICIAN, JR | 14 | 12 | 0 | 0 | 0 | 2
2 | ARCHITECTURAL PROJECT SUPERINTENDENT | 1 | 1 | 0 | 0 | 0 | 0 | 3 | FINISHING CARPENTER | 6 | 5 | 0 | 1 | 0 | 0
3 | SR. PROJECT ARCHITECT | 1 | 1 | 0 | 0 | 0 | 0 | 4 | FINISHING MASON | 38 | 38 | 0 | 0 | 0 | 0
4 | PROJECT ARCHITECT | 1 | 1 | 0 | 0 | 0 | 0 | 5 | FOREMAN (MASON) | 1 | 1 | 0 | 0 | 0 | 0
5 | PROJECT ENGINEER (MEPFS) | 2 | 1 | 0 | 0 | 0 | 1 | 6 | FOREMAN (MEPFS) | 3 | 3 | 0 | 0 | 0 | 0
6 | SR. QA/QC ARCHITECT | 1 | 1 | 0 | 0 | 0 | 0 | 7 | FOREMAN (SCAFFOLDER) | 1 | 1 | 0 | 0 | 0 | 0
7 | QUANTITY SURVEYOR | 1 | 0 | 1 | 0 | 0 | 0 | 8 | FOREMAN ARCHITECTURAL | 1 | 1 | 0 | 0 | 0 | 0
8 | SR. QUANTITY SURVEYOR | 1 | 0 | 0 | 0 | 0 | 1 | 9 | HELPER(WAREHOUSE PLUMBER) | 1 | 1 | 0 | 0 | 0 | 0
9 | PRECAST ENGINEER (rescue) | 1 | 0 | 1 | 0 | 0 | 0 | 10 | INSTALLER | 23 | 20 | 2 | 1 | 0 | 0
| SubTotal | 10 | 5 | 2 | 0 | 0 | 3 | 11 | LEADMAN CARPENTER | 1 | 1 | 0 | 0 | 0 | 0
[8 empty] | 12 | LEADMAN DATAWALL INSTALLER | 2 | 2 | 0 | 0 | 0 | 0
B. LINE & GRADE / SURVEY TEAM |  | R | P | A | OL | AS | NR | 13 | LEADMAN ELECTRICIAN | 2 | 2 | 0 | 0 | 0 | 0
1 | INSTRUMENTMAN | 1 | 1 | 0 | 0 | 0 | 0 | 14 | LEADMAN INSTALLER | 4 | 4 | 0 | 0 | 0 | 0
2 | SURVEY AIDE | 2 | 2 | 0 | 0 | 0 | 0 | 15 | LEADMAN LABORER | 4 | 3 | 1 | 0 | 0 | 0
| SubTotal | 3 | 3 | 0 | 0 | 0 | 0 | 16 | LEADMAN MASON | 6 | 4 | 1 | 1 | 0 | 0
[8 empty] | 17 | LEADMAN PAINTER | 10 | 9 | 0 | 0 | 0 | 1
C. ADMINISTRATIVE & CLERICAL WORKS |  | R | P | A | OL | AS | NR | 18 | LEADMAN PLUMBER | 3 | 2 | 1 | 0 | 0 | 0
1 | DOCUMENT CONTROL CLERK | 1 | 0 | 0 | 0 | 0 | 1 | 19 | LEADMAN SCAFFOLDER | 2 | 2 | 0 | 0 | 0 | 0
2 | PROJECT ADMIN OFFICER | 1 | 1 | 0 | 0 | 0 | 0 | 20 | LEADMAN SEALANT APPLICATOR | 1 | 1 | 0 | 0 | 0 | 0
3 | TIMEKEEPER, JR. | 1 | 0 | 0 | 0 | 0 | 1 | 21 | LEADMAN TILESETTER | 1 | 1 | 0 | 0 | 0 | 0
4 | WAREHOUSEMAN, JR. | 1 | 1 | 0 | 0 | 0 | 0 | 22 | LEADMAN WELDER | 1 | 0 | 0 | 0 | 0 | 1
5 | QA/QC AIDE | 1 | 1 | 0 | 0 | 0 | 0 | 23 | PAINTER | 87 | 79 | 5 | 2 | 0 | 1
6 | TIMEKEEPER AIDE | 1 | 1 | 0 | 0 | 0 | 0 | 24 | PLUMBER, JR | 22 | 19 | 1 | 1 | 0 | 1
7 | UTILITY/MESSENGER | 2 | 2 | 0 | 0 | 0 | 0 | 25 | SCAFFOLDER | 18 | 17 | 1 | 0 | 0 | 0
8 | WAREHOUSE AIDE | 4 | 3 | 1 | 0 | 0 | 0 | 26 | SEALANT APPLICATOR | 5 | 4 | 0 | 1 | 0 | 0
| SubTotal | 12 | 9 | 1 | 0 | 0 | 2 | 27 | TILESETTER | 25 | 23 | 1 | 0 | 0 | 1
[8 empty] | 28 | WELDER | 3 | 3 | 0 | 0 | 0 | 0
D. SAFETY |  | R | P | A | OL | AS | NR | TOTAL DIRECT |  | 290 | 263 | 13 | 7 | 0 | 7
1 | SAFETY ENFORCER | 1 | 1 | 0 | 0 | 0 | 0
| SubTotal | 1 | 1 | 0 | 0 | 0 | 0 | DISTRIBUTION OF LABORER |  | Roster | Present | Absent | On Leave | AS | NR
[8 empty] | 1 | DFOR ENCODER(MEPFS) | 1 | 1 | 0 | 0 | 0 | 0
E. EQUIPMENT OPERATORS |  | R | P | A | OL | AS | NR | 2 | DOORMAN | 7 | 7 | 0 | 0 | 0 | 0
1 | TRUCK DRIVER (Alberto P. Mangaoang) | 1 | 1 | 0 | 0 | 0 | 0 | 3 | FORMWORKS WAREHOUSE | 4 | 4 | 0 | 0 | 0 | 0
2 | DRIVER 1 (Joseph B. Chu) | 1 | 1 | 0 | 0 | 0 | 0 | 4 | HAULER | 14 | 8 | 3 | 3 | 0 | 0
3 | SERVICE DRIVER (OSIAS C. ADVINCULA) | 1 | 1 | 0 | 0 | 0 | 0 | 5 | HOUSEKEEPING/SAFETY CREW | 2 | 2 | 0 | 0 | 0 | 0
4 | SERVICE ELEVATOR OPERATOR | 1 | 1 | 0 | 0 | 0 | 0 | 6 | SCAFFOLDER | 1 | 1 | 0 | 0 | 0 | 0
5 | SKID LOADER OPERATOR | 1 | 1 | 0 | 0 | 0 | 0 | 7 | TIMEKEEPER AIDE | 2 | 2 | 0 | 0 | 0 | 0
| SubTotal | 5 | 5 | 0 | 0 | 0 | 0 | 8 | UTILITY/MESSENGER | 1 | 1 | 0 | 0 | 0 | 0
[8 empty] | 9 | WAREHOUSE ADMIN | 1 | 1 | 0 | 0 | 0 | 0
F. MAINTENANCE |  | R | P | A | OL | AS | NR | 10 | WELDER | 3 | 0 | 0 | 0 | 0 | 3
1 | ELECTRICIAN, JR | 1 | 1 | 0 | 0 | 0 | 0 | 11 | FINISHING MASON | 1 | 1 | 0 | 0 | 0 | 0
2 | PLUMBER, JR | 1 | 1 | 0 | 0 | 0 | 0 | TOTAL |  | 37 | 28 | 3 | 3 | 0 | 3
| SubTotal | 2 | 2 | 0 | 0 | 0 | 0
NIGHT SHIFT
NIGHT SHIFT from PREVIOUS DATE |  | 2018-11-21 | [5 empty] | 1 | LABORER | 0 | 0 | 0 | 0 | 0 | 0
INDIRECT LABOR |  | Roster | Present | Absent | On Leave | AS | NR | TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0
A. ADMINISTRATIVE & CLERICAL WORKS
B. EQUIPMENT OPERATORS AND MAINTENANCE | [7 empty] | SUBCONTRACTOR |  | R | P | A | OL | AS | NR
1 | MAINTENANCE(ELECTRICIAN, JR) | 1 | 1 | 0 | 0 | 0 | 0 | 1 | TRES MARIAS (TPI) | 4 | 3 | 1 | 0 | 0 | 0
2 | MAINTENANCE(PLUMBER, JR) | 1 | 1 | 0 | 0 | 0 | 0 | 2 | CITIAIRE INDUSTRIAL SERVICES CORPORATION | 9 | 0 | 9 | 0 | 0 | 0
3 | LEADMAN LABORER | 0 | 0 | 0 | 0 | 0 | 0 | 3 | LM INTEGRATED SYSTEMS & DATA NETWORKING INC. | 6 | 5 | 1 | 0 | 0 | 0
4 | PLUMBER, JR(WAREHOUSE PLUMBER) | 1 | 1 | 0 | 0 | 0 | 0 | 4 | JOMCC | 6 | 0 | 6 | 0 | 0 | 0
5 | WAREHOUSE AIDE | 1 | 1 | 0 | 0 | 0 | 0 | 5 | I-CONSTECH | 5 | 5 | 0 | 0 | 0 | 0
TOTAL INDIRECT |  | 4 | 4 | 0 | 0 | 0 | 0 | 6 | GEMWOOD EAST TRADING CORPORATION | 10 | 6 | 4 | 0 | 0 | 0
[8 empty] | 7 | JEFF JAMES INC | 45 | 0 | 45 | 0 | 0 | 0
[8 empty] | 8 | INTEGRATED BUILDERS & WATERPROOFING TECHNOLOGY | 10 | 4 | 6 | 0 | 0 | 0
RESCUE WORKERS FROM OTHER PROJECT |  | Roster | Present | Absent | On Leave | AS | NR | 9 | WESWIN COMPANY INC. | 7 | 5 | 2 | 0 | 0 | 0
1 | LABORER(HELPER) | 3 | 2 | 1 | 0 | 0 | 0 | 10 | GUANCO MARBLE | 5 | 0 | 5 | 0 | 0 | 0
2 | FINISHING MASON | 5 | 2 | 1 | 2 | 0 | 0 | 11 | FABRIWELD BUILDING SYSTEM INC | 5 | 0 | 5 | 0 | 0 | 0
| TOTAL RESCUE | 8 | 4 | 2 | 2 | 0 | 0 | 12 | DALKIA | 7 | 5 | 2 | 0 | 0 | 0
[8 empty] | 13 | JGL | 7 | 0 | 7 | 0 | 0 | 0
TOTAL SUMMARY |  | Roster | Present | Absent | On Leave | AS | NR | 14 | J.VAZ.CO | 6 | 0 | 6 | 0 | 0 | 0
Indirect Labor |  | 33 | 25 | 3 | 0 | 0 | 5 | 15 | LEVEL LAND COPR. | 5 | 0 | 5 | 0 | 0 | 0
Indirect Labor(prev. date) |  | 4 | 4 | 0 | 0 | 0 | 0 |  | TOTAL SUBCON | 137 | 33 | 104 | 0 | 0 | 0
Direct Labor |  | 327 | 291 | 16 | 10 | 0 | 10
Direct Labor(prev. date) |  | 0 | 0 | 0 | 0 | 0 | 0
Subcontractor |  | 137 | 33 | 104 | 0 | 0 | 0 | Legend: | R-Roster, P-Present, A-Absent, OL-On Leave, AS-Administrative Suspension, NR-Not Required, D/S-Day Shift, N/S-Night Shift, M/S-Mid Shift, NS-No Submission, OC-On Call, NA-No Activity
Rescue Workers |  | 8 | 4 | 2 | 2 | 0 | 0
GRAND TOTAL |  | 509 | 357 | 125 | 12 | 0 | 15
[8 empty] | Prepared by: |  | Noted by:
[8 empty] | SHERYLL ROSE A. BRIOSO |  | JOSEPH BRYAN T. MANALOTO
[8 empty] | Jr. Timekeeper |  | Project Manager

## Sheet2
WEATHER CHART
AM | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
PM | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| FAIR |  |  | CLOUDY |  |  | RAINY |  |  | WINDY

## Sheet4
SUNDAY OVERTIME